## README
Northgate Constructors Ltd. — Synthetic Corporate Finance Dataset
PURPOSE: Practice / portfolio dataset for building a WIP & project financial dashboard in Power BI.
ALL DATA IS FICTIONAL. Generated for demonstration purposes — no real company, client, or project data.
SHEETS:
Projects — master list: contract values, revised values (orig + approved COs), current cost estimates
Job_Cost_Detail — monthly costs by project and category (Labour / Materials / Subcontracts / Equipment)
Billings — monthly progress billings by project
Change_Orders — CO register with Approved / Pending status (only Approved COs revise contract value)
WIP_Schedule — live percentage-of-completion schedule built from the sheets above (all formulas)
KEY CONCEPTS (percentage-of-completion method):
% Complete = Cost to Date / Estimated Total Cost
Earned Revenue = % Complete x Revised Contract Value
Over/(Under) Billing = Billed to Date - Earned Revenue (over = liability, under = asset)
Margin fade = Est. GP% falling vs original — watch P-106 Larkspur (thin margin) and P-104 (negative billing bias)
DASHBOARD IDEAS: WIP table with drill-down · GP% trend by project · over/under billing waterfall ·
approved vs pending CO exposure · cost mix by category · revenue by client / sector / district

## Projects
Project ID | Project Name | Client | Sector | District | Original Contract Value | Approved Change Orders | Revised Contract Value | Estimated Total Cost (Current)
P-101 | Riverbend Water Treatment Expansion | City of Meadowvale | Civil | Prairies | 48500000 | 0 | 48500000 | 44620000
P-102 | Aurora Logistics Distribution Centre | NorthStar Logistics | Buildings | Prairies | 23400000 | 1199000 | 24599000 | 22877000
P-103 | Kestrel Ridge Wind Farm BOP | Kestrel Renewables | Industrial | Prairies | 86000000 | 0 | 86000000 | 80840000
P-104 | St. Bridget Hospital Renovation Ph2 | Vantage Health Partners | Buildings | Mountain | 31750000 | 0 | 31750000 | 28892000
P-105 | Coyote Flats Gas Processing Module | TriPeak Midstream | Industrial | Mountain | 112000000 | 6424000 | 118424000 | 112503000
P-106 | Larkspur Transit Garage | Metro Transit Authority | Civil | Pacific | 19800000 | 1346000 | 21146000 | 20723000
P-107 | Meridian Office Tower Fit-Out | Meridian Properties | Buildings | Pacific | 12600000 | 411000 | 13011000 | 11450000
P-108 | Signal Hill Substation Upgrade | Prairie Grid Corp | Industrial | Prairies | 27300000 | 0 | 27300000 | 25116000

## Job_Cost_Detail
Month End | Project ID | Cost Category | Amount
2025-07-28 | P-101 | Labour | 606568
2025-07-28 | P-101 | Materials | 522598
2025-07-28 | P-101 | Subcontracts | 337902
2025-07-28 | P-101 | Equipment | 152722
2025-08-28 | P-101 | Labour | 838626
2025-08-28 | P-101 | Materials | 806004
2025-08-28 | P-101 | Subcontracts | 521437
2025-08-28 | P-101 | Equipment | 234297
2025-09-28 | P-101 | Labour | 873518
2025-09-28 | P-101 | Materials | 604742
2025-09-28 | P-101 | Subcontracts | 403708
2025-09-28 | P-101 | Equipment | 253576
2025-10-28 | P-101 | Labour | 1678671
2025-10-28 | P-101 | Materials | 1190629
2025-10-28 | P-101 | Subcontracts | 896668
2025-10-28 | P-101 | Equipment | 378303
2025-11-28 | P-101 | Labour | 1547660
2025-11-28 | P-101 | Materials | 1242521
2025-11-28 | P-101 | Subcontracts | 764601
2025-11-28 | P-101 | Equipment | 396561
2025-12-28 | P-101 | Labour | 1623862
2025-12-28 | P-101 | Materials | 1242360
2025-12-28 | P-101 | Subcontracts | 772649
2025-12-28 | P-101 | Equipment | 406614
2026-01-28 | P-101 | Labour | 695814
2026-01-28 | P-101 | Materials | 581860
2026-01-28 | P-101 | Subcontracts | 357620
2026-01-28 | P-101 | Equipment | 179109
2026-02-28 | P-101 | Labour | 1324316
2026-02-28 | P-101 | Materials | 917198
2026-02-28 | P-101 | Subcontracts | 604632
2026-02-28 | P-101 | Equipment | 263852
2026-03-28 | P-101 | Labour | 648559
2026-03-28 | P-101 | Materials | 578784
2026-03-28 | P-101 | Subcontracts | 350577
2026-03-28 | P-101 | Equipment | 171097
2026-04-28 | P-101 | Labour | 988314
2026-04-28 | P-101 | Materials | 628910
2026-04-28 | P-101 | Subcontracts | 392309
2026-04-28 | P-101 | Equipment | 215552
2026-05-28 | P-101 | Labour | 1446563
2026-05-28 | P-101 | Materials | 1065804
2026-05-28 | P-101 | Subcontracts | 602953
2026-05-28 | P-101 | Equipment | 334110
2026-06-28 | P-101 | Labour | 660496
2026-06-28 | P-101 | Materials | 466185
2026-06-28 | P-101 | Subcontracts | 308959
2026-06-28 | P-101 | Equipment | 170266
2025-07-28 | P-102 | Labour | 593418
2025-07-28 | P-102 | Materials | 444761
2025-07-28 | P-102 | Subcontracts | 317555
2025-07-28 | P-102 | Equipment | 150018
2025-08-28 | P-102 | Labour | 809125
2025-08-28 | P-102 | Materials | 644807
2025-08-28 | P-102 | Subcontracts | 390802
2025-08-28 | P-102 | Equipment | 177344
2025-09-28 | P-102 | Labour | 1213279
2025-09-28 | P-102 | Materials | 902494
2025-09-28 | P-102 | Subcontracts | 601032
2025-09-28 | P-102 | Equipment | 274920
2025-10-28 | P-102 | Labour | 837964
2025-10-28 | P-102 | Materials | 750840
2025-10-28 | P-102 | Subcontracts | 477156
2025-10-28 | P-102 | Equipment | 201395
2025-11-28 | P-102 | Labour | 397514
2025-11-28 | P-102 | Materials | 365004
2025-11-28 | P-102 | Subcontracts | 249077
2025-11-28 | P-102 | Equipment | 130066
2025-12-28 | P-102 | Labour | 1074440
2025-12-28 | P-102 | Materials | 872061
2025-12-28 | P-102 | Subcontracts | 461149
2025-12-28 | P-102 | Equipment | 258454
2026-01-28 | P-102 | Labour | 1045326
2026-01-28 | P-102 | Materials | 747809
2026-01-28 | P-102 | Subcontracts | 489454
2026-01-28 | P-102 | Equipment | 246330
2026-02-28 | P-102 | Labour | 903607
2026-02-28 | P-102 | Materials | 788909
2026-02-28 | P-102 | Subcontracts | 462802
2026-02-28 | P-102 | Equipment | 217060
2026-03-28 | P-102 | Labour | 532684
2026-03-28 | P-102 | Materials | 474099
2026-03-28 | P-102 | Subcontracts | 319287
2026-03-28 | P-102 | Equipment | 132525
2026-04-28 | P-102 | Labour | 511263
2026-04-28 | P-102 | Materials | 378690
2026-04-28 | P-102 | Subcontracts | 278811
2026-04-28 | P-102 | Equipment | 147501
2026-05-28 | P-102 | Labour | 493038
2026-05-28 | P-102 | Materials | 389966
2026-05-28 | P-102 | Subcontracts | 271602
2026-05-28 | P-102 | Equipment | 124611
2026-06-28 | P-102 | Labour | 362216
2026-06-28 | P-102 | Materials | 245443
2026-06-28 | P-102 | Subcontracts | 195188
2026-06-28 | P-102 | Equipment | 89079
2025-07-28 | P-103 | Labour | 1565697
2025-07-28 | P-103 | Materials | 1024187
2025-07-28 | P-103 | Subcontracts | 769945
2025-07-28 | P-103 | Equipment | 352565
2025-08-28 | P-103 | Labour | 2020493
2025-08-28 | P-103 | Materials | 1450821
2025-08-28 | P-103 | Subcontracts | 1002263
2025-08-28 | P-103 | Equipment | 495513
2025-09-28 | P-103 | Labour | 705486
2025-09-28 | P-103 | Materials | 485769
2025-09-28 | P-103 | Subcontracts | 343751
2025-09-28 | P-103 | Equipment | 153680
2025-10-28 | P-103 | Labour | 993441
2025-10-28 | P-103 | Materials | 869849
2025-10-28 | P-103 | Subcontracts | 527148
2025-10-28 | P-103 | Equipment | 261009
2025-11-28 | P-103 | Labour | 1010376
2025-11-28 | P-103 | Materials | 794147
2025-11-28 | P-103 | Subcontracts | 445418
2025-11-28 | P-103 | Equipment | 233286
2025-12-28 | P-103 | Labour | 1632654
2025-12-28 | P-103 | Materials | 1299139
2025-12-28 | P-103 | Subcontracts | 699029
2025-12-28 | P-103 | Equipment | 413240
2026-01-28 | P-103 | Labour | 795325
2026-01-28 | P-103 | Materials | 756717
2026-01-28 | P-103 | Subcontracts | 387382
2026-01-28 | P-103 | Equipment | 200719
2026-02-28 | P-103 | Labour | 752301
2026-02-28 | P-103 | Materials | 543022
2026-02-28 | P-103 | Subcontracts | 456453
2026-02-28 | P-103 | Equipment | 188750
2026-03-28 | P-103 | Labour | 1095959
2026-03-28 | P-103 | Materials | 863527
2026-03-28 | P-103 | Subcontracts | 565426
2026-03-28 | P-103 | Equipment | 317413
2026-04-28 | P-103 | Labour | 1005956
2026-04-28 | P-103 | Materials | 793050
2026-04-28 | P-103 | Subcontracts | 573873
2026-04-28 | P-103 | Equipment | 256508
2026-05-28 | P-103 | Labour | 803602
2026-05-28 | P-103 | Materials | 682707
2026-05-28 | P-103 | Subcontracts | 529828
2026-05-28 | P-103 | Equipment | 264751
2026-06-28 | P-103 | Labour | 811388
2026-06-28 | P-103 | Materials | 618937
2026-06-28 | P-103 | Subcontracts | 501589
2026-06-28 | P-103 | Equipment | 247306
2025-07-28 | P-104 | Labour | 747436
2025-07-28 | P-104 | Materials | 547777
2025-07-28 | P-104 | Subcontracts | 381051
2025-07-28 | P-104 | Equipment | 211197
2025-08-28 | P-104 | Labour | 651928
2025-08-28 | P-104 | Materials | 593099
2025-08-28 | P-104 | Subcontracts | 304794
2025-08-28 | P-104 | Equipment | 183228
2025-09-28 | P-104 | Labour | 526909
2025-09-28 | P-104 | Materials | 369883
2025-09-28 | P-104 | Subcontracts | 317216
2025-09-28 | P-104 | Equipment | 124574
2025-10-28 | P-104 | Labour | 640984
2025-10-28 | P-104 | Materials | 417140
2025-10-28 | P-104 | Subcontracts | 356764
2025-10-28 | P-104 | Equipment | 166389
2025-11-28 | P-104 | Labour | 546131
2025-11-28 | P-104 | Materials | 433043
2025-11-28 | P-104 | Subcontracts | 278230
2025-11-28 | P-104 | Equipment | 122575
2025-12-28 | P-104 | Labour | 881042
2025-12-28 | P-104 | Materials | 498899
2025-12-28 | P-104 | Subcontracts | 369401
2025-12-28 | P-104 | Equipment | 203468
2026-01-28 | P-104 | Labour | 331180
2026-01-28 | P-104 | Materials | 271430
2026-01-28 | P-104 | Subcontracts | 185791
2026-01-28 | P-104 | Equipment | 87421
2026-02-28 | P-104 | Labour | 667605
2026-02-28 | P-104 | Materials | 607232
2026-02-28 | P-104 | Subcontracts | 335424
2026-02-28 | P-104 | Equipment | 180817
2026-03-28 | P-104 | Labour | 446957
2026-03-28 | P-104 | Materials | 300852
2026-03-28 | P-104 | Subcontracts | 216526
2026-03-28 | P-104 | Equipment | 110277
2026-04-28 | P-104 | Labour | 794290
2026-04-28 | P-104 | Materials | 541998
2026-04-28 | P-104 | Subcontracts | 322701
2026-04-28 | P-104 | Equipment | 185618
2026-05-28 | P-104 | Labour | 639463
2026-05-28 | P-104 | Materials | 550547
2026-05-28 | P-104 | Subcontracts | 372133
2026-05-28 | P-104 | Equipment | 153500
2026-06-28 | P-104 | Labour | 329823
2026-06-28 | P-104 | Materials | 230740
2026-06-28 | P-104 | Subcontracts | 191129
2026-06-28 | P-104 | Equipment | 84378
2025-07-28 | P-105 | Labour | 3038766
2025-07-28 | P-105 | Materials | 2098396
2025-07-28 | P-105 | Subcontracts | 1415214
2025-07-28 | P-105 | Equipment | 598581
2025-08-28 | P-105 | Labour | 1397048
2025-08-28 | P-105 | Materials | 945795
2025-08-28 | P-105 | Subcontracts | 704574
2025-08-28 | P-105 | Equipment | 338038
2025-09-28 | P-105 | Labour | 1011496
2025-09-28 | P-105 | Materials | 845758
2025-09-28 | P-105 | Subcontracts | 473456
2025-09-28 | P-105 | Equipment | 267827
2025-10-28 | P-105 | Labour | 1698488
2025-10-28 | P-105 | Materials | 1235822
2025-10-28 | P-105 | Subcontracts | 979690
2025-10-28 | P-105 | Equipment | 465604
2025-11-28 | P-105 | Labour | 2069957
2025-11-28 | P-105 | Materials | 1479709
2025-11-28 | P-105 | Subcontracts | 1069815
2025-11-28 | P-105 | Equipment | 559403
2025-12-28 | P-105 | Labour | 2355500
2025-12-28 | P-105 | Materials | 1982028
2025-12-28 | P-105 | Subcontracts | 1304503
2025-12-28 | P-105 | Equipment | 552906
2026-01-28 | P-105 | Labour | 2158060
2026-01-28 | P-105 | Materials | 1873982
2026-01-28 | P-105 | Subcontracts | 1023061
2026-01-28 | P-105 | Equipment | 494173
2026-02-28 | P-105 | Labour | 3000411
2026-02-28 | P-105 | Materials | 2054710
2026-02-28 | P-105 | Subcontracts | 1549207
2026-02-28 | P-105 | Equipment | 709947
2026-03-28 | P-105 | Labour | 2313148
2026-03-28 | P-105 | Materials | 1599591
2026-03-28 | P-105 | Subcontracts | 1259593
2026-03-28 | P-105 | Equipment | 666472
2026-04-28 | P-105 | Labour | 1456094
2026-04-28 | P-105 | Materials | 922873
2026-04-28 | P-105 | Subcontracts | 733225
2026-04-28 | P-105 | Equipment | 355708
2026-05-28 | P-105 | Labour | 2020363
2026-05-28 | P-105 | Materials | 1193654
2026-05-28 | P-105 | Subcontracts | 798996
2026-05-28 | P-105 | Equipment | 444112
2026-06-28 | P-105 | Labour | 2640250
2026-06-28 | P-105 | Materials | 2255442
2026-06-28 | P-105 | Subcontracts | 1372616
2026-06-28 | P-105 | Equipment | 764333
2025-07-28 | P-106 | Labour | 571385
2025-07-28 | P-106 | Materials | 479110
2025-07-28 | P-106 | Subcontracts | 335032
2025-07-28 | P-106 | Equipment | 126449
2025-08-28 | P-106 | Labour | 978128
2025-08-28 | P-106 | Materials | 836813
2025-08-28 | P-106 | Subcontracts | 462712
2025-08-28 | P-106 | Equipment | 238106
2025-09-28 | P-106 | Labour | 415200
2025-09-28 | P-106 | Materials | 329541
2025-09-28 | P-106 | Subcontracts | 223711
2025-09-28 | P-106 | Equipment | 114871
2025-10-28 | P-106 | Labour | 458183
2025-10-28 | P-106 | Materials | 333617
2025-10-28 | P-106 | Subcontracts | 241739
2025-10-28 | P-106 | Equipment | 125331
2025-11-28 | P-106 | Labour | 702925
2025-11-28 | P-106 | Materials | 535788
2025-11-28 | P-106 | Subcontracts | 315368
2025-11-28 | P-106 | Equipment | 175141
2025-12-28 | P-106 | Labour | 403951
2025-12-28 | P-106 | Materials | 338757
2025-12-28 | P-106 | Subcontracts | 256179
2025-12-28 | P-106 | Equipment | 104373
2026-01-28 | P-106 | Labour | 497935
2026-01-28 | P-106 | Materials | 360140
2026-01-28 | P-106 | Subcontracts | 281144
2026-01-28 | P-106 | Equipment | 117804
2026-02-28 | P-106 | Labour | 711842
2026-02-28 | P-106 | Materials | 480817
2026-02-28 | P-106 | Subcontracts | 347588
2026-02-28 | P-106 | Equipment | 139983
2026-03-28 | P-106 | Labour | 511442
2026-03-28 | P-106 | Materials | 501046
2026-03-28 | P-106 | Subcontracts | 253222
2026-03-28 | P-106 | Equipment | 126204
2026-04-28 | P-106 | Labour | 707810
2026-04-28 | P-106 | Materials | 472036
2026-04-28 | P-106 | Subcontracts | 338767
2026-04-28 | P-106 | Equipment | 150986
2026-05-28 | P-106 | Labour | 368475
2026-05-28 | P-106 | Materials | 286432
2026-05-28 | P-106 | Subcontracts | 205088
2026-05-28 | P-106 | Equipment | 113213
2026-06-28 | P-106 | Labour | 847350
2026-06-28 | P-106 | Materials | 666741
2026-06-28 | P-106 | Subcontracts | 482329
2026-06-28 | P-106 | Equipment | 265917
2025-07-28 | P-107 | Labour | 168273
2025-07-28 | P-107 | Materials | 116516
2025-07-28 | P-107 | Subcontracts | 84766
2025-07-28 | P-107 | Equipment | 45136
2025-08-28 | P-107 | Labour | 105838
2025-08-28 | P-107 | Materials | 78091
2025-08-28 | P-107 | Subcontracts | 51309
2025-08-28 | P-107 | Equipment | 27973
2025-09-28 | P-107 | Labour | 126043
2025-09-28 | P-107 | Materials | 75335
2025-09-28 | P-107 | Subcontracts | 63897
2025-09-28 | P-107 | Equipment | 26464
2025-10-28 | P-107 | Labour | 103622
2025-10-28 | P-107 | Materials | 69242
2025-10-28 | P-107 | Subcontracts | 59423
2025-10-28 | P-107 | Equipment | 24316
2025-11-28 | P-107 | Labour | 118297
2025-11-28 | P-107 | Materials | 103818
2025-11-28 | P-107 | Subcontracts | 65874
2025-11-28 | P-107 | Equipment | 28977
2025-12-28 | P-107 | Labour | 117868
2025-12-28 | P-107 | Materials | 68239
2025-12-28 | P-107 | Subcontracts | 55381
2025-12-28 | P-107 | Equipment | 25887
2026-01-28 | P-107 | Labour | 173985
2026-01-28 | P-107 | Materials | 124672
2026-01-28 | P-107 | Subcontracts | 90669
2026-01-28 | P-107 | Equipment | 36585
2026-02-28 | P-107 | Labour | 153828
2026-02-28 | P-107 | Materials | 125490
2026-02-28 | P-107 | Subcontracts | 81007
2026-02-28 | P-107 | Equipment | 41210
2026-03-28 | P-107 | Labour | 70995
2026-03-28 | P-107 | Materials | 59507
2026-03-28 | P-107 | Subcontracts | 34826
2026-03-28 | P-107 | Equipment | 17303
2026-04-28 | P-107 | Labour | 159832
2026-04-28 | P-107 | Materials | 136774
2026-04-28 | P-107 | Subcontracts | 97308
2026-04-28 | P-107 | Equipment | 40846
2026-05-28 | P-107 | Labour | 149708
2026-05-28 | P-107 | Materials | 120235
2026-05-28 | P-107 | Subcontracts | 70647
2026-05-28 | P-107 | Equipment | 32782
2026-06-28 | P-107 | Labour | 149052
2026-06-28 | P-107 | Materials | 113021
2026-06-28 | P-107 | Subcontracts | 74165
2026-06-28 | P-107 | Equipment | 35048
2025-07-28 | P-108 | Labour | 171343
2025-07-28 | P-108 | Materials | 141873
2025-07-28 | P-108 | Subcontracts | 83679
2025-07-28 | P-108 | Equipment | 37614
2025-08-28 | P-108 | Labour | 175450
2025-08-28 | P-108 | Materials | 149837
2025-08-28 | P-108 | Subcontracts | 92273
2025-08-28 | P-108 | Equipment | 56285
2025-09-28 | P-108 | Labour | 110694
2025-09-28 | P-108 | Materials | 79372
2025-09-28 | P-108 | Subcontracts | 55752
2025-09-28 | P-108 | Equipment | 23530
2025-10-28 | P-108 | Labour | 220245
2025-10-28 | P-108 | Materials | 186232
2025-10-28 | P-108 | Subcontracts | 128520
2025-10-28 | P-108 | Equipment | 52753
2025-11-28 | P-108 | Labour | 173951
2025-11-28 | P-108 | Materials | 138039
2025-11-28 | P-108 | Subcontracts | 74020
2025-11-28 | P-108 | Equipment | 37049
2025-12-28 | P-108 | Labour | 202796
2025-12-28 | P-108 | Materials | 147102
2025-12-28 | P-108 | Subcontracts | 95627
2025-12-28 | P-108 | Equipment | 55364
2026-01-28 | P-108 | Labour | 161717
2026-01-28 | P-108 | Materials | 140105
2026-01-28 | P-108 | Subcontracts | 93298
2026-01-28 | P-108 | Equipment | 43365
2026-02-28 | P-108 | Labour | 172453
2026-02-28 | P-108 | Materials | 123526
2026-02-28 | P-108 | Subcontracts | 83211
2026-02-28 | P-108 | Equipment | 44850
2026-03-28 | P-108 | Labour | 160830
2026-03-28 | P-108 | Materials | 129659
2026-03-28 | P-108 | Subcontracts | 84550
2026-03-28 | P-108 | Equipment | 33552
2026-04-28 | P-108 | Labour | 120440
2026-04-28 | P-108 | Materials | 85797
2026-04-28 | P-108 | Subcontracts | 52481
2026-04-28 | P-108 | Equipment | 24860
2026-05-28 | P-108 | Labour | 102283
2026-05-28 | P-108 | Materials | 67729
2026-05-28 | P-108 | Subcontracts | 45062
2026-05-28 | P-108 | Equipment | 19732
2026-06-28 | P-108 | Labour | 231173
2026-06-28 | P-108 | Materials | 167555
2026-06-28 | P-108 | Subcontracts | 109156
2026-06-28 | P-108 | Equipment | 51763

## Billings
Month End | Project ID | Amount Billed
2025-07-28 | P-101 | 1885600
2025-08-28 | P-101 | 2861100
2025-09-28 | P-101 | 2596400
2025-10-28 | P-101 | 4457700
2026-01-28 | P-101 | 1892700
2026-02-28 | P-101 | 2908300
2026-03-28 | P-101 | 1914800
2026-04-28 | P-101 | 2290200
2026-05-28 | P-101 | 3682400
2026-06-28 | P-101 | 1811000
2025-07-28 | P-102 | 1419200
2025-08-28 | P-102 | 2013000
2025-09-28 | P-102 | 2727500
2025-10-28 | P-102 | 2452200
2025-11-28 | P-102 | 1165600
2025-12-28 | P-102 | 3102500
2026-01-28 | P-102 | 2652400
2026-03-28 | P-102 | 1570400
2026-04-28 | P-102 | 1622000
2026-05-28 | P-102 | 1342000
2026-06-28 | P-102 | 1106700
2025-08-28 | P-103 | 4405300
2025-09-28 | P-103 | 2088000
2025-10-28 | P-103 | 3155200
2025-11-28 | P-103 | 2711700
2025-12-28 | P-103 | 4636300
2026-01-28 | P-103 | 2464500
2026-02-28 | P-103 | 2247600
2026-03-28 | P-103 | 3147500
2026-04-28 | P-103 | 3079700
2026-06-28 | P-103 | 2322500
2025-07-28 | P-104 | 2111600
2025-08-28 | P-104 | 1688700
2025-09-28 | P-104 | 1522900
2025-10-28 | P-104 | 1506100
2025-11-28 | P-104 | 1629000
2025-12-28 | P-104 | 1975700
2026-01-28 | P-104 | 812800
2026-02-28 | P-104 | 2125400
2026-03-28 | P-104 | 1012700
2026-04-28 | P-104 | 2140900
2026-05-28 | P-104 | 1730300
2026-06-28 | P-104 | 965200
2025-07-28 | P-105 | 7252800
2025-08-28 | P-105 | 3689000
2025-09-28 | P-105 | 3005200
2025-10-28 | P-105 | 4787700
2025-11-28 | P-105 | 5445800
2025-12-28 | P-105 | 6402700
2026-01-28 | P-105 | 6278700
2026-02-28 | P-105 | 7280400
2026-03-28 | P-105 | 6895200
2026-04-28 | P-105 | 3648600
2026-05-28 | P-105 | 4876300
2026-06-28 | P-105 | 7388100
2025-07-28 | P-106 | 1515100
2025-08-28 | P-106 | 2654500
2025-09-28 | P-106 | 989600
2025-10-28 | P-106 | 1241300
2025-11-28 | P-106 | 1628200
2025-12-28 | P-106 | 1125400
2026-01-28 | P-106 | 1254900
2026-02-28 | P-106 | 1543500
2026-03-28 | P-106 | 1584300
2026-04-28 | P-106 | 1712700
2026-05-28 | P-106 | 1059800
2026-06-28 | P-106 | 2574300
2025-07-28 | P-107 | 477800
2025-08-28 | P-107 | 318200
2025-09-28 | P-107 | 332900
2025-10-28 | P-107 | 323700
2025-12-28 | P-107 | 306400
2026-01-28 | P-107 | 491700
2026-02-28 | P-107 | 486800
2026-03-28 | P-107 | 199400
2026-04-28 | P-107 | 511000
2026-06-28 | P-107 | 445200
2025-07-28 | P-108 | 431200
2025-09-28 | P-108 | 278700
2025-10-28 | P-108 | 628500
2025-11-28 | P-108 | 414800
2025-12-28 | P-108 | 591200
2026-01-28 | P-108 | 523700
2026-02-28 | P-108 | 439600
2026-03-28 | P-108 | 406400
2026-04-28 | P-108 | 319900
2026-06-28 | P-108 | 691200

## Change_Orders
Project ID | CO # | Date | Description | Status | Amount
P-102 | CO-01 | 2025-11-28 | Added electrical scope | Approved | 477000
P-102 | CO-02 | 2025-10-28 | Differing site conditions | Approved | 567000
P-102 | CO-03 | 2026-03-28 | Added electrical scope | Pending | 696000
P-102 | CO-04 | 2026-04-28 | Added electrical scope | Approved | 155000
P-104 | CO-01 | 2026-01-28 | Added electrical scope | Pending | 697000
P-105 | CO-01 | 2025-10-28 | Design revision | Approved | 1969000
P-105 | CO-02 | 2025-09-28 | Owner-directed scope addition | Approved | 1268000
P-105 | CO-03 | 2026-02-28 | Schedule acceleration | Approved | 3187000
P-105 | CO-04 | 2025-10-28 | Schedule acceleration | Pending | 3232000
P-106 | CO-01 | 2026-04-28 | Schedule acceleration | Approved | 441000
P-106 | CO-02 | 2026-01-28 | Added electrical scope | Approved | 290000
P-106 | CO-03 | 2026-01-28 | Schedule acceleration | Approved | 473000
P-106 | CO-04 | 2025-12-28 | Design revision | Approved | 142000
P-107 | CO-01 | 2025-12-28 | Owner-directed scope addition | Pending | 255000
P-107 | CO-02 | 2025-12-28 | Owner-directed scope addition | Pending | 356000
P-107 | CO-03 | 2025-10-28 | Added electrical scope | Approved | 411000

## WIP_Schedule
Project ID | Project Name | Revised Contract Value | Est. Total Cost | Cost to Date | % Complete | Earned Revenue | Billed to Date | Over/(Under) Billing | Est. Gross Profit | Est. GP % | Cost to Complete
P-101 | Riverbend Water Treatment Expansion | 48500000 | 44620000 | 32250636 | 72.28% | 35055039.1304 | 26300200 | -8754839.1304 | 3880000 | 8% | 12369364
P-102 | Aurora Logistics Distribution Centre | 24599000 | 22877000 | 22441975 | 98.1% | 24131229.7515 | 21173500 | -2957729.7515 | 1722000 | 7% | 435025
P-103 | Kestrel Ridge Wind Farm BOP | 86000000 | 80840000 | 33561395 | 41.52% | 35703611.7021 | 30258300 | -5445311.7021 | 5160000 | 6% | 47278605
P-104 | St. Bridget Hospital Renovation Ph2 | 31750000 | 28892000 | 18010990 | 62.34% | 19792639.2254 | 19221300 | -571339.2254 | 2858000 | 9.002% | 10881010
P-105 | Coyote Flats Gas Processing Module | 118424000 | 112503000 | 62548395 | 55.6% | 65840298.743 | 66950500 | 1110201.257 | 5921000 | 5% | 49954605
P-106 | Larkspur Transit Garage | 21146000 | 20723000 | 18336721 | 88.48% | 18711012.0285 | 18883600 | 172587.9715 | 423000 | 2% | 2386279
P-107 | Meridian Office Tower Fit-Out | 13011000 | 11450000 | 4000080 | 34.94% | 4545418.4175 | 3893100 | -652318.4175 | 1561000 | 12% | 7449920
P-108 | Signal Hill Substation Upgrade | 27300000 | 25116000 | 5038547 | 20.06% | 5476681.5217 | 4725200 | -751481.5217 | 2184000 | 8% | 20077453
| TOTAL | 370730000 | 347021000 | 196188739 | 56.54% | 209255930.5201 | 191405700 | -17850230.5201 | 23709000 | 6.395% | 150832261
All formulas — nothing hardcoded. Source data: Projects / Job_Cost_Detail / Billings / Change_Orders sheets.